## Traceability Matrix
Traceability Matrix
Project Name: | Blood Drive
Project Number: | Team 3
Project Manager:
Purpose: To manage requirements throughout the software development lifecycle. The Traceabilty Matrix ensures that requirements are captured in the design, implemented in the code, and verified by testing.
Requirement Number | Requirement Description | Applicable Roles | Test Case | Priority | Status | Comments | Duration
B1 | Login to the Application | User and Admin | TC01,TC02, TC03,TC04 | High | Pass | As expected | 1hr
B2 | Registration | User | TC05,TC06, TC07,TC08, TC09,TC10 | High | Pass | As expected | 1hr
B3 | Donar registration | User | TC10,TC11, TC12,TC13, TC14 | Low | Pass | As expected | 2hrs
B4 | Donar Search | User | TC15,TC16, TC17,TC18, TC19 | High | Pass | As expected | 2hrs
B5 | My Profile | User and Admin | TC20,TC21 | High | Pass | As expected | 4hrs
B6 | Updation | User and Admin | TC22,TC23 | Low | Pass | As expected | 5hrs
B7 | Deletion | User and Admin | TC24,TC25 | Low | Pass | As expected | 1hr
B8 | Inbox | User | TC26,TC27 | Low | Pass | As expected | 3hrs
B9 | Logout from the Application | User and Admin | TC28,TC29 | High | Pass | As expected | 1hr
Note on C9: Tip: Consider using status indicators such as “In Progress, Proposed, Approved, Implemented, Verified, and Deleted”
Note on D9: Tip: Identify the design component that is associated with the requirement

## Field Instructions
Tracability Matrix Instructions
Field | Description
Requirement Number | List the number of the tracable requirement.
Requirement Description | Provide a description of the individual requirement that is being traced throughout the software development lifecycle.
Design Component / Module | Identify the corresponding design component / module that addresses the tracable requirement.
Status | Identify the status of the requirement. Consider using status indicators such as “Proposed, Approved, Implemented, Verified, and Deleted”
Test Cases | List the test cases that address the tracable requirement.
Comments | Provide any comments that help to trace the requirements through the software development lifecycle.